PROJECT STRATOSPHERE: MIGRATION SPECIFICATIONS

Client: Cloudio LLC

Source: Microsoft Azure (East US)

Destination: AWS (US-East-1)

1. SERVICE MAPPING STRATEGY

--------------------------------------------------

A. Compute

- Source: Azure Virtual Machines (D-Series)

- Target: Amazon EC2 (m6i.large and m6i.xlarge instances)

- Strategy: Rehost (Lift & Shift) using AWS Application Migration Service (MGN).

B. Storage (Object)

- Source: Azure Blob Storage (Hot Tier)

- Target: Amazon S3 (Standard Class)

- Tooling: AWS DataSync (configured to pull from Azure via SAS tokens).

C. Databases

- Source: Azure SQL Database

- Target: Amazon RDS for SQL Server (Enterprise Edition)

- Note: We will use the AWS Schema Conversion Tool (SCT) to analyze for any proprietary stored procedures that might conflict.

D. Networking

- Source: Azure VNet

- Target: AWS VPC (Virtual Private Cloud)

- Connectivity: 1Gbps AWS Direct Connect established between Azure ExpressRoute and AWS to facilitate high-speed data transfer.

E. Identity Management

- Source: Azure Active Directory (Entra ID)

- Target: AWS IAM Identity Center (formerly SSO)

- Integration: Configure SAML 2.0 federation so users keep existing Azure AD credentials to log into AWS.

2. CRITICAL MIGRATION PHASES

--------------------------------------------------

Phase 1: Discovery (Current Phase)

- Deploy AWS Discovery Agents to catalog all running processes and network connections.

- Tag all Azure resources to separate "Migrate," "Retire," and "Archive" workloads.

Phase 2: Foundation

- Build AWS Landing Zone using Control Tower.

- Establish Subnets (Public/Private) and Security Groups (Firewalls).

- Test Direct Connect link latency.

Phase 3: The Pilot (HR Portal)

- Migrate the internal HR application.

- Validate success/failure logs.

- Benchmarking: Compare performance cost of Azure D-Series vs AWS m6i.

Phase 4: Production Waves

- Wave 1: Non-critical backend services (Logging, Archival).

- Wave 2: Customer-facing Web App (Blue/Green deployment).

- Wave 3: Primary Transactional Databases (Requires 4-hour maintenance window).

3. KNOWN CHALLENGES & MITIGATIONS

--------------------------------------------------

- Challenge: Azure Service Bus dependency.

- Mitigation: Temporary bridge using RabbitMQ on EC2 until code is refactored for Amazon SQS.

- Challenge: Hardcoded IP addresses in legacy code.

- Mitigation: Code audit using grep/regex scripts to identify and replace IPs with DNS hostnames before migration.

- Challenge: Data Egress Fees.

- Mitigation: Negotiate with Azure for egress waiver if applicable, or factor standard data transfer rates into the Q4 budget.